## Introduction
Project Information Checklist
for Stream Engineering, Management and Restoration Project Proposals
Concept
The intent of the checklist is to determine whether sufficient and appropriate information has been provided by a project sponsor to perform a project review. Additionally, it may serve as the basis for development of a comprehensive Biological Assessment. Use of the checklist, by both project reviewers and project sponsors, is intended to:
· clarify reporting expectations,
· streamline the review process,
· facilitate consistency among project proposals and their review, and
· promote thorough reporting that enables review.
Introduction
For project reviewers, the checklist is formatted to assist in determining whether all the information suggested to support effective project review has been provided. Thorough and thoughtful project reporting is a first and significant step in facilitating an effective and efficient review process. The logic inherent in the checklist is that a project that provides the suggested level of documentation has of necessity conducted project appraisal and design with a reasonable degree of integrity. Clearly, the checklist implies a substantive effort on the part of project sponsors, and it may lead to a more detailed review. However, if the checklist/template is widely adopted, efficiencies (in terms of time taken to prepare the proposal and consistency of review) can be expected in the future.
For project sponsors and their design teams, the checklist clarifies reporting expectations, provides a framework for review, and supplies a template for reporting and, eventually, Biological Assessment documentation. Initially, it may appear to project proponents that the checklist will increase the burden of reporting requirements. However, once the advantages of the checklist approach are realized, it will be recognized as a template and reporting standard; something which design practice representatives have suggested is currently lacking. As it currently stands, sponsors and design teams often have different expectations with respect to consultation reporting and documentation, especially from region to region.
How the checklist may be used
The checklist will provide the greatest value in the hands of project sponsors/designers as a template for reporting. For Services staff, using the checklist to identify gaps in the reported information will highlight elements of review that may need additional consideration or consultation. Clearly, not all the information listed in the checklist will be relevant or even appropriate for every project. A column of NA (not applicable) check boxes is provided. Thus, the checklist can be adapted to varying reporting requirements.

## Checklist
Item # | Yes - Sufficient | No - Insufficient | NA - Not Applicable |  | page # in submittal
| Y | N | NA | PROJECT SPONSOR AND TEAM | Page
1 | ¨ | ¨ | ¨ | Project owner
2 | ¨ | ¨ | ¨ | Project contact
3 | ¨ | ¨ | ¨ | Applicant and relation to project owner
4 | ¨ | ¨ | ¨ | Project design team and relation to project owner
5 | ¨ | ¨ | ¨ | Project funding
| Y | N | NA | ESA SECTION 7 AND CONSULTATION HISTORY | Page
6 | ¨ | ¨ | ¨ | Status of all listed or candidate species within project stream
7 | ¨ | ¨ | ¨ | Presence of either designated critical habitat or EFH within stream
8 | ¨ | ¨ | ¨ | Summary of informal consultation history to date
EXISTING CONDITIONS AND CONTEXT
| Y | N | NA | Watershed scale conditions and project context | Page
9 | ¨ | ¨ | ¨ | Description of past, present, and anticipated future land use impacts
10 | ¨ | ¨ | ¨ | Description of enduring biogenic impacts: beaver removal, introduced species, diseases
11 | ¨ | ¨ | ¨ | Climate change impacts observed to date or predicted (especially in glaciated basins)
12 | ¨ | ¨ | ¨ | Watershed map showing limiting features: passage barriers, dams, levees, diversions, etc.
13 | ¨ | ¨ | ¨ | Description of beaver history in project area and vicinity and current status of beaver
14 | ¨ | ¨ | ¨ | Description of existing native aquatic species populations
15 | ¨ | ¨ | ¨ | Description of water quality (including temperature) and constraints and limitations
16 | ¨ | ¨ | ¨ | Description of nutrient status, constraints and limitations
| Y | N | NA | Reach scale conditions and context | Page
17 | ¨ | ¨ | ¨ | Description of past and present impacts on channel, riparian and floodplain conditions
18 | ¨ | ¨ | ¨ | Water quality condition, constraints and description of causes of impacts
19 | ¨ | ¨ | ¨ | Instream flow management and constraints in the project reach
20 | ¨ | ¨ | ¨ | Description of geomorphic conditions and constraints on physical processes
21 | ¨ | ¨ | ¨ | Description of riparian condition and historical riparian impacts
22 | ¨ | ¨ | ¨ | Description of lateral connectivity to floodplain and historical floodplain impacts
23 | ¨ | ¨ | ¨ | Tidal influence in project reach and influence of structural controls (dikes or gates)
24 | ¨ | ¨ | ¨ | Non-project actions (on-going or planned) that may affect listed species
25 | ¨ | ¨ | ¨ | Non-project actions (on-going or planned) that may affect project outcome
DESCRIPTION OF PROPOSED ACTION
| Y | N | NA | WHAT (General) - Project description | Page
26 | ¨ | ¨ | ¨ | Project goal statement
27 | ¨ | ¨ | ¨ | Project objectives
28 | ¨ | ¨ | ¨ | Project schedule
29 | ¨ | ¨ | ¨ | Characterization as a restoration, rehabilitation, enhancement, or stabilization
30 | ¨ | ¨ | ¨ | Description of any related/interdependent actions, or statement that none exist
31 | ¨ | ¨ | ¨ | Description of all complementary or associated conservation strategies
| Y | N | NA | WHAT (specific) - Project elements and details | Page
32 | ¨ | ¨ | ¨ | List of primary project elements
33 | ¨ | ¨ | ¨ | Expected functional life of each element in terms of its “deformability”
34 | ¨ | ¨ | ¨ | Timeframe until fully functional for each project element
35 | ¨ | ¨ | ¨ | Description of risk that element will fail to perform as intended and consequences
36 | ¨ | ¨ | ¨ | Disturbance and impacts associated with implementation of each element
| Y | N | NA | WHY - Evaluation of Need and Justification | Page
37 | ¨ | ¨ | ¨ | Description of identified problems, and their causes, addressed by project
38 | ¨ | ¨ | ¨ | Relation of proposed actions to existing watershed or recovery plan priorities
39 | ¨ | ¨ | ¨ | Description of how listed/candidate or target species will benefit
40 | ¨ | ¨ | ¨ | List of alternatives considered and summary of alternatives analysis.
41 | ¨ | ¨ | ¨ | Description of existing and future threats (potential impacts not yet realized).
| Y | N | NA | WHERE - Action area | Page
42 | ¨ | ¨ | ¨ | USGS stream name and river mile from mouth; coordinates; 6th field HUC
43 | ¨ | ¨ | ¨ | Watershed map showing location of proposed action
44 | ¨ | ¨ | ¨ | Watershed map showing distribution of listed species, Critical Habitat, EFH
45 | ¨ | ¨ | ¨ | Watershed map of “action area” over which effects of the actions will be felt
46 | ¨ | ¨ | ¨ | Ownership of adjacent and affected lands, including those needed for access
DESCRIPTION OF PROPOSED ACTION Cont'd
| Y | N | NA | HOW - Construction and Implementation | Page
47 | ¨ | ¨ | ¨ | List of required permits and status of each permit application
48 | ¨ | ¨ | ¨ | Plan sheets that identify all project elements and construction activities
49 | ¨ | ¨ | ¨ | List of all materials and their sources and quantities
50 | ¨ | ¨ | ¨ | Construction dewatering design criteria and plan
51 | ¨ | ¨ | ¨ | Soil erosion and sediment control plan.
52 | ¨ | ¨ | ¨ | Description of best management practices that will be implemented.
53 | ¨ | ¨ | ¨ | List proposed equipment and provide fuels management plan.
54 | ¨ | ¨ | ¨ | Description of how aquatic organisms within the action area will be treated/protected.
| Y | N | NA | WHEN - Schedule for implementation | Page
55 | ¨ | ¨ | ¨ | Project schedule including permits, implementation, monitoring, and outcomes.
56 | ¨ | ¨ | ¨ | Calendar schedule for construction/implementation procedures.
DESIGN DOCUMENTATION
| Y | N | NA | Design team | Page
57 | ¨ | ¨ | ¨ | Name and titles of firms and individuals responsible for design.
58 | ¨ | ¨ | ¨ | List of project elements that have been designed by a licensed Professional Engineer.
| Y | N | NA | Hydrologic analysis | Page
59 | ¨ | ¨ | ¨ | Description of historic, ongoing, or anticipated impacts to basin hydrologic regime.
60 | ¨ | ¨ | ¨ | Summary of hydrologic analyses conducted, including data sources and period of record.
61 | ¨ | ¨ | ¨ | List design discharge (Q) and return interval (RI) for each design element.
| Y | N | NA | Sediment transport and dynamics analysis | Page
62 | ¨ | ¨ | ¨ | Description of previous or anticipated impacts to basin or reach sediment supply.
63 | ¨ | ¨ | ¨ | Summary of sediment supply and transport analyses conducted, including data sources.
64 | ¨ | ¨ | ¨ | Describe sediment size gradation used in streambed design.
| Y | N | NA | Hydraulic analysis | Page
65 | ¨ | ¨ | ¨ | Summary of hydraulic modeling or analyses conducted and data source.
66 | ¨ | ¨ | ¨ | Inundation map for design and flood flows before and after implementation.
| Y | N | NA | Vegetation design | Page
67 | ¨ | ¨ | ¨ | Species list, materials sources, and plant form.
68 | ¨ | ¨ | ¨ | Planting plan map (distribution and density by species) and irrigation plan.
| Y | N | NA | Soils and geotechnical analysis | Page
69 | ¨ | ¨ | ¨ | Summary of geotechnical analyses including stratigraphy and grain size of materials.
70 | ¨ | ¨ | ¨ | Groundwater elevation, flow direction and seasonality within floodplain and banks.
| Y | N | NA | MONITORING AND MANAGEMENT PLAN | Page
71 | ¨ | ¨ | ¨ | Monitoring plan that specifies evaluation of project success relative to objectives.
72 | ¨ | ¨ | ¨ | Monitoring schedule in relation to anticipated timeframe for achieving project objectives.
73 | ¨ | ¨ | ¨ | Adaptive management plan specific to each project objective.
EFFECTS ANALYSIS - WHAT IS AT RISK?
| Y | N | NA | Habitat | Page
74 | ¨ | ¨ | ¨ | Describe worst-case consequences of any project elements on habitat access.
75 | ¨ | ¨ | ¨ | Describe worst-case consequences of any elements on quantity or quality of habitat.
76 | ¨ | ¨ | ¨ | Description of probability of occurrence and how that probability was determined.
77 | ¨ | ¨ | ¨ | Description of actions that might be taken to reduce the probability or consequences.
| Y | N | NA | Channel Process | Page
78 | ¨ | ¨ | ¨ | Describe worst-case consequences of any project elements on natural channel processes.
79 | ¨ | ¨ | ¨ | Describe worst-case consequences of any project elements on watershed controls.
80 | ¨ | ¨ | ¨ | Description of probability of occurrence and how that probability was determined.
81 | ¨ | ¨ | ¨ | Description of actions that might be taken to reduce the probability or consequences.
| Y | N | NA | Water quality | Page
82 | ¨ | ¨ | ¨ | Describe worst-case consequences of any project elements on water quality.
83 | ¨ | ¨ | ¨ | Description of probability of occurrence and how that probability was determined.
84 | ¨ | ¨ | ¨ | Description of actions that might be taken to reduce the probability or consequences.
Note on B3: Peter Skidmore: Yes - Sufficient
Note on B9: Peter Skidmore: Yes - Sufficient
Note on B14: Peter Skidmore: Yes - Sufficient
Note on B23: Peter Skidmore: Yes - Sufficient
Note on B34: Peter Skidmore: Yes - Sufficient
Note on B41: Peter Skidmore: Yes - Sufficient
Note on B47: Peter Skidmore: Yes - Sufficient
Note on B53: Peter Skidmore: Yes - Sufficient
Note on B60: Peter Skidmore: Yes - Sufficient
Note on B69: Peter Skidmore: Yes - Sufficient
Note on B73: Peter Skidmore: Yes - Sufficient
Note on B76: Peter Skidmore: Yes - Sufficient
Note on B80: Peter Skidmore: Yes - Sufficient
Note on B84: Peter Skidmore: Yes - Sufficient
Note on B87: Peter Skidmore: Yes - Sufficient
Note on B90: Peter Skidmore: Yes - Sufficient
Note on B93: Peter Skidmore: Yes - Sufficient
Note on B97: Peter Skidmore: Yes - Sufficient
Note on B98: Peter Skidmore: Yes - Sufficient
Note on B103: Peter Skidmore: Yes - Sufficient
Note on B108: Peter Skidmore: Yes - Sufficient
Note on C3: Peter Skidmore: NO - Insufficient
Note on C9: Peter Skidmore: NO - Insufficient
Note on C14: Peter Skidmore: NO - Insufficient
Note on C23: Peter Skidmore: NO - Insufficient
Note on C34: Peter Skidmore: NO - Insufficient
Note on C41: Peter Skidmore: NO - Insufficient
Note on C47: Peter Skidmore: NO - Insufficient
Note on C53: Peter Skidmore: NO - Insufficient
Note on C60: Peter Skidmore: NO - Insufficient
Note on C69: Peter Skidmore: NO - Insufficient
Note on C73: Peter Skidmore: NO - Insufficient
Note on C76: Peter Skidmore: NO - Insufficient
Note on C80: Peter Skidmore: NO - Insufficient
Note on C84: Peter Skidmore: NO - Insufficient
Note on C87: Peter Skidmore: NO - Insufficient
Note on C90: Peter Skidmore: NO - Insufficient
Note on C93: Peter Skidmore: NO - Insufficient
Note on C97: Peter Skidmore: NO - Insufficient
Note on C98: Peter Skidmore: NO - Insufficient
Note on C103: Peter Skidmore: NO - Insufficient
Note on C108: Peter Skidmore: NO - Insufficient
Note on D3: Peter Skidmore: NA - Not Applicable
Note on D9: Peter Skidmore: NA - Not Applicable
Note on D14: Peter Skidmore: NA - Not Applicable
Note on D23: Peter Skidmore: NA - Not Applicable
Note on D34: Peter Skidmore: NA - Not Applicable
Note on D41: Peter Skidmore: NA - Not Applicable
Note on D47: Peter Skidmore: NA - Not Applicable
Note on D53: Peter Skidmore: NA - Not Applicable
Note on D60: Peter Skidmore: NA - Not Applicable
Note on D69: Peter Skidmore: NA - Not Applicable
Note on D73: Peter Skidmore: NA - Not Applicable
Note on D76: Peter Skidmore: NA - Not Applicable
Note on D80: Peter Skidmore: NA - Not Applicable
Note on D84: Peter Skidmore: NA - Not Applicable
Note on D87: Peter Skidmore: NA - Not Applicable
Note on D90: Peter Skidmore: NA - Not Applicable
Note on D93: Peter Skidmore: NA - Not Applicable
Note on D97: Peter Skidmore: NA - Not Applicable
Note on D98: Peter Skidmore: NA - Not Applicable
Note on D103: Peter Skidmore: NA - Not Applicable
Note on D108: Peter Skidmore: NA - Not Applicable
Note on E13: Peter Skidmore: This section lists suggested information to describe pre-action conditions and the watershed, geomorphic, planning, social, and constraints contexts within which the project will be implemented. It is intended to meet the requirements for reporting the ‘Environmental baseline’, a term fairly narrowly interpreted by NOAA in an ESA context. It is also intended to be a comprehensive examination of “context” as described in the underpinning science document
Note on E14: Peter Skidmore: The watershed extends from the headwaters of the project stream to its mouth or confluence with a higher order stream. Reporting of watershed scale conditions is important to justifying the actions in the watershed and planning contexts and to considering potential impacts beyond the project reach.
Note on E23: Peter Skidmore: Reach scale information addresses site-specific impacts or habitat deficiencies that justify the proposed project, as well as existing constraints such as infrastructure that may limit alternatives. A “reach” includes the project site and up- and downstream for a distance at least equal to the project length.
Note on E33: Peter Skidmore: This section lists information needed to understand the proposed actions and specific project elements to facilitate review of probable effects.
Note on E59: Peter Skidmore: This section lists information needed to understand the proposed actions and specific project elements to facilitate review of probable effects.
Note on E97: Peter Skidmore: This section examines whether the project proponent has considered risk to water quality, habitat access, habitat quantity/quality, channel processes, and watershed condition/controls, as a direct or indirect consequence of the project actions
Note on F3: Peter Skidmore: Page number in submitted proposal
Note on F9: Peter Skidmore: Page number in submitted proposal
Note on F14: Peter Skidmore: Page number in submitted proposal
Note on F23: Peter Skidmore: Page number in submitted proposal
Note on F34: Peter Skidmore: Page number in submitted proposal
Note on F41: Peter Skidmore: Page number in submitted proposal
Note on F47: Peter Skidmore: Page number in submitted proposal
Note on F53: Peter Skidmore: Page number in submitted proposal
Note on F60: Peter Skidmore: Page number in submitted proposal
Note on F69: Peter Skidmore: Page number in submitted proposal
Note on F73: Peter Skidmore: Page number in submitted proposal
Note on F76: Peter Skidmore: Page number in submitted proposal
Note on F80: Peter Skidmore: Page number in submitted proposal
Note on F84: Peter Skidmore: Page number in submitted proposal
Note on F87: Peter Skidmore: Page number in submitted proposal
Note on F90: Peter Skidmore: Page number in submitted proposal
Note on F93: Peter Skidmore: Page number in submitted proposal
Note on F97: Peter Skidmore: Page number in submitted proposal
Note on F98: Peter Skidmore: Page number in submitted proposal
Note on F103: Peter Skidmore: Page number in submitted proposal
Note on F108: Peter Skidmore: Page number in submitted proposal

## Instructions
Project Information Checklist
for Stream Engineering, Management and Restoration Project Proposals
General
The checklist provides check-columns for 'Yes-Sufficient Information'; 'No-Insufficient Information'; or 'NA - Not Applicable'. To place an 'x' in the box, select the cell, then type 'x'
The check boxes are "Wingding" font symbols. They will fill with an 'x' if you type an 'x'. But if you delete the cell, the 'x' and the checkbox will go away. If you make an error, use Command 'z' to undo the error, or copy and paste a check box from an empty cell into the cell you want to correct.
This is an unprotected worksheet, feel free to edit it for your specific needs, but keep in mind that the formatting and organization can easily be changed by mistake. Use command+Z to retract the most recent entry, rather than delete.
Recording your comments
To record comments, scroll to the right for a column field. This will print as a separate page, but comments will be numbered to correspond with the item numbers for each item in the checklist. Pages are numbered such that checklist items are odd-numbered pages and comments for those items are on the following even-numbered page.